RESEARCH PROGRESS MEMO

Calibrating the Crowd: Assessing Prediction Market Accuracy Through Sports Betting Markets

To: Professor Arend Kuyper      From: Dylan Ryan      Date: July 31, 2026      Re: Progress to date (weeks 1–5 of 8)

The short version

The proposal asked whether sports prediction markets are calibrated forecasting tools or just another way to gamble. Measurement is done, and the answer came back stronger than the question: a CFTC-regulated exchange (Kalshi), an offshore crypto market (Polymarket Global), the de-vigged sportsbook consensus (~10.5 books/game), and — added this week — Polymarket’s separately regulated US entity all produce formally equivalent, well-calibrated, coherent, unexploitable forecasts on the same games. The one big difference is cost: exchanges charge ~1% where books charge ~4.2%. I’m about two weeks ahead of the roadmap; every number now regenerates from raw data with one command (38 analyses, ~2 min, 0 failures), a full code review + data audit is behind me, and report drafting starts this week.

What I’ve done

Data & pipeline.

- Built collectors for all sources: 9,482-game ESPN registry (7 leagues, May 2025–Jul 2026); Kalshi closing prices for 9,186 games (order-book mids; trade-reconstruction beyond the 60-day API retention); Polymarket CLOB prices for 5,563; book consensus for 5,151. Clean three-way joint set: n = 5,328; four-way (with Polymarket US public tape): n = 2,639.

- Depth layers: 28,940 Kalshi alternate-spread contracts, 107,100 book alternate-line points, 710K per-fill trades, 7-horizon price paths on ~8,000 games, T−24h “opening” book consensus (3,461 games), plus a live 15-min VPS collector (now with order-book depth) and a World Cup 3-way case study.

- Rigor infrastructure: a 48-check data-quality gate plus a deep coherence audit (look-ahead, side-flip, clock, misattachment checks) run as the first modules of the suite — currently 72 checks, 0 warnings; a regenerated FDR inventory (12 of 13 positive claims survive BH at q=0.05).

Headline results.

- A statistical dead heat: Briers 0.2196 / 0.2199 / 0.2196 (K/P/book), all pairwise date-clustered DM tests n.s., and TOST-equivalent at δ = 0.001 Brier — pooled, within each big league, at every horizon in the final day, and under every proper scoring function (Murphy diagrams, sup-t bands). Sharpness is equal too; no favorite–longshot bias anywhere; ladders 97.3% monotone; no strategy clears costs.

- The fourth leg (this week): Polymarket US — a legally disjoint, US-only pool — is TOST-equivalent to each of the other three, and its prices sit a median 0.50pt from Global’s even though nobody can arbitrage the two: a law of one price across segregated pools, i.e., shared information, not shared traders.

- Markets beat a walk-forward Elo model built from public win/loss records by ~14×10⁻³ Brier (z≈7.4) while differing from each other by ≤0.5×10⁻³ — equally good, and equally better than public statistics.

- Mechanism results: the equivalence is built during the final day (books hold a small real lead at T−24h, p=0.020, closed by start); no venue leads at 15-min or 1-min resolution — big repricings are simultaneous; price discovery is maker-driven (aggressive flow carries no signal). Bürgi–Deng–Whelan’s platform-wide pathologies (−20% ROI, longshot cliff) vanish in sports — the one Kalshi corner with a professional benchmark.

- One clean crack, contained: Kalshi’s thin MLB run-line ladders under-price small margins by +8.4pts where books price the same cell to +0.4 — but selling the mispriced side loses 2.9–4.5% net of fees. Biases persist only inside transaction-cost bands, the way books harbor biases inside the vig.

- A natural experiment: Polymarket’s 2026-03-30 sports fee left accuracy untouched (DiD p=0.74) but cut relative taker volume ~41% at the fee date — fees moved quantity, not price quality.

Issues I ran into (and what they taught me)

- Side-assignment contamination. An “impossible” backtest profit exposed ~350 games with mis-assigned sides (team-code alias collisions). Fixed with a ticker-order rule validated 99.6% against ESPN. The pre-fix data said “Kalshi significantly lags the books” (p=0.004); clean data says equivalence — the project’s best methods lesson, and it goes in the report.

- Self-audit findings. A full code/methodology review (Jul 30, 23 verified findings) caught real problems: a stale FDR inventory, a push-scoring bug, a tie-handling bias in the book PIT, an inverted sign label, silently dropped franchises (Clippers/Canadiens/Blues — name-matching bugs, ~290 games since re-collected). I retracted two claims outright (the MLB 45.0% run-line figure was a push-scoring artifact; an NBA encompassing sub-claim died as n grew) and downgraded the “Kalshi carries extra information” whisper to suggestive. Every headline conclusion survived every fix.

- Perishable data. Kalshi discards price history past ~60 days, so a biweekly re-harvest is load-bearing; API budgets (Odds API credits, OddPool’s 770 req/mo) forced dry-run cost estimates before every backfill; Polymarket’s volume archive has a March coverage gap that the fee analysis has to work around.

Decisions I’ve made

- Report every p-value from the conservative choice (date-clustered), use Shin de-vig for anything tail-sensitive (multiplicative de-vig provably distorts tails), and pre-commit to a BH-FDR discipline over positive claims.

- Frame the paper around “gambling venue or forecasting institution?” — never “can you beat it?” Exploitability appears only as an institutional diagnostic. Working synthesis: sportsbook-like at the retail-taker surface, forecasting instrument in aggregate.

- Treat Polymarket Global and Polymarket US as distinct institutions (different regulators, disjoint pools) — which turned a data-labeling question into the design’s cleanest mechanism test.

- Retract loudly, in writing, with the reason — findings.md carries its own corrections log.

Where I’d value your input

- The seven methodology questions from the Jul 21 checkpoint are still open: two-family FDR/TOST policy; the δ=0.001 TOST margin convention; interval-randomized PIT; date-only vs two-way clustering; lead–lag formality (regressions + event study vs Hasbrouck shares); RPS for the 3-way case study; and sign-off on the organizing frame above. Happy to take rulings by email — any of them can change report text.

- Logistics: is the target the grant report alone or also a venue (arXiv / Journal of Prediction Markets)? First full draft lands ~Aug 3 — what turnaround works for comments? And any concerns with making the repo public after secret rotation (book data shipped as code + instructions)?

Plan to Aug 24

Weeks 6–7: write the report from the finished skeleton (every cited number pulled from regenerated logs — no hand-carried values), two review cycles if the first draft reaches you by ~Aug 8. Week 8: reproducibility packaging — secret rotation, README + data-availability note, public repo, archive, retire the VPS collector. Standing chores continue: biweekly Kalshi re-harvest (~Aug 4), weekly VPS sync, and a final lead–lag + first price-of-immediacy pass on the accumulated depth series mid-August.